## Slide 1: COVID-19 Organ Authorization
Carlie House BSN, MHA
Director of Donor and Family Support
Notes: Want to share our vision for the future of PE
Provide transparency and further build trust
The goals are to:
Share our vision for the future of our department
Provide the opportunity for questions
Seek input
Gain championship of the LT

## Slide 2
  The COVID-19 pandemic has significantly altered how we approach for organ authorization. This has resulted in a favorable approach outcome of merely 14% (1 out of 7) for non-FPA patients in the final two weeks of March, a drastic decrease compared to the typical outcome of 60%. In this PDSA, we plan to identify the barriers to organ authorization which COVID-19 has introduced and develop countermeasures to mitigate those adverse effects. In doing so, organ authorization will be optimized during the time of the pandemic which will result in more organs being transplanted and more lives saved.
Reason for Action
Notes: Advocate for the transformation – set the expectation at every level and ensure PEA can integrate

## Slide 3
What is Different for FSS with COVID-19?
Hospital operations
Attitudes of hospital staff
Patient families
MT Family Support Specialists
Notes: Advocate for the transformation – set the expectation at every level and ensure PEA can integrate

## Slide 4
Cycle 1 Solution Approaches
Gap | # | If We… | Then We…
MT Process Changes | 1 | Proactively communicate to hospital and families regarding realistic timeline | Increased authorization; families and hospitals will give us more time; more organs allocated
Family Support Stressors | 8 | Weekly coffee team meetings to support one another | Help staff remain focused and encouraged
 | 11 | Provide Skype training Re: Phone approaches Role-playing Verbiage How to slow down (phone silence) Presumptive language for non-FPA | Staff more comfortable and confident approaching over the phone; more authorization;
Family Changes | 16 | Pro-actively offer to call other family members; e.g. set-up multi-party line | More support for the families; more consents; (group decisions/support)
 | 17 | Offer to meet the entire family group outdoors | 
Notes: Advocate for the transformation – set the expectation at every level and ensure PEA can integrate

## Slide 5
Cycle 2: Solution Approaches
Gap | If We… | Then We…
Variation in debriefing with AC | Debrief all “no” Debrief all difficult “yes” All employees with < 1 yr approach experience AC will document debriefing and lessons learned in PDSA Data Tracking Tool and in email between Approach Coaches | Enhance learning for entire team
Variation in confidence when approaching families | Read book or listen to podcast to inspire confidence | Will equip FSS to build their confidence in approaching families
Masks create communication barriers (and families not able / willing to meet outside the patient room) | Acquiring “see-through” masks Develop standard verbiage acknowledging the situation to mitigate effects of masks (human connection) Model: Acknowledge the facts Acknowledge my own feelings Apologize briefly Example: “I am sitting right in front of you, we can see each other, but I feel so far away from you because we have these masks on and I’m so sorry.” | Can show more empathy to families during in-person approaches
Notes: Advocate for the transformation – set the expectation at every level and ensure PEA can integrate

## Slide 6
Insights & Learnings from PDSA
What went well?
  In April and May, we experienced some of our highest authorization rates ever
  In May, we tied the record for the most organs transplanted in a month
  During the pandemic, the importance of every “yes” has been made clearer for everyone
  Delayed funerals has removed the rush to make arrangements
  FSS not going out to the hospital on every referral has reduced their burden and resulted in rejuvenation
  FSS team was willing to jump into phone approaching even though it was brand new for all of them
  It is great to see the fruit of our efforts; and we can apply these learnings post-pandemic
  We worked through a lot very quickly with very little lead time
What did we learn?
  Donation gives families some control at hospital during COVID-19
  Limited visiting hours has taken away families’ expectations to be with their loved one throughout the donation process, which has taken away some time constraints
  Phone approaches are not hurting us and may be helping us (scheduled time of withdraw has helped us get in front of DCD)
  Communicating confidence on the phone is very significant; families perceive “we know what we’re doing”
  Training others has helped me with phone approaches
  Focus = Results (can be simple things)
  Moved Non-FPA authorization from 42% in March to 60% in April to 71% in May!
Notes: Advocate for the transformation – set the expectation at every level and ensure PEA can integrate